## How to use
Animation Shot Tracker
A free animation shot spreadsheet: track shots by sequence and stage with artist, status, and retakes in Google Sheets and Excel.
Quick start
1 | Open the Shots tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | One row per shot with its current pipeline stage; Due turns red when passed and the shot is not approved.
3 | Bid days versus actual days shows where the schedule is slipping; Over bid turns amber.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Shots
Sequence | Shot | Frames | Stage | Artist | Status | Due | Bid days | Actual days | Seconds | Over bid
SQ010 Opening | sh010 | 96 | Polish | Ana | Ready for review | 2026-10-14 | 4 | 4 | 4 | 0
SQ010 Opening | sh020 | 140 | Spline | Ben | In progress | 2026-10-16 | 5 | 4 | 5.8 | 0
SQ020 Chase | sh010 | 72 | Blocking | Cara | Notes | 2026-10-12 | 3 | 4 | 3 | 1
SQ020 Chase | sh020 | 210 | Layout | Dev | In progress | 2026-10-19 | 6 | 1 | 8.8 | 0
SQ030 Finale | sh010 | 180 | Comp | Eli | Approved | 2026-10-11 | 4 | 4 | 7.5 | 0

## Production
Item | Value | Notes
Progress
Shots | 5
Approved | 1
Seconds approved | 7.5
Budget
Total bid days | 22
Days over bid | 1