## How to use
Asbestos Abatement Job Tracker
A free job tracker for asbestos abatement: schedule jobs, log area and material, and track containment status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Track each job through notification, containment, abatement and clearance; Promised turns red when the finish date passes.
3 | File regulatory notifications (NESHAP and state) by their deadlines before work starts.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Site | Stage | Supervisor | Promised | Price | Deposit | Material | Area (sq ft) | Balance | Days open
2026-09-23 | Fairview School District | Fairview MS boiler room | Abatement | R. Diaz | 2026-10-16 | 18400 | 5000 | Pipe insulation | 1200 | 13400 | 19
2026-10-01 | Harbor Properties | Unit 4B, 200 Main St | Containment | T. Moore | 2026-10-18 | 4600 | 1500 | Popcorn ceiling | 850 | 3100 | 11
2026-10-05 | Kline | 18 Elm St basement | Notification filed | R. Diaz | 2026-10-23 | 3200 | 1000 | Floor tile and mastic | 400 | 2200 | 7
2026-09-03 | City of Fairview | Old library annex | Air clearance | T. Moore | 2026-10-12 | 26500 | 8000 | Duct wrap | 2200 | 18500 | 39
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Survey | 0
Stage: Notification filed | 1
Stage: Containment | 1
Stage: Abatement | 1
Stage: Air clearance | 1
Stage: Complete | 0
Totals
Total price | 52700
Total deposit | 15500
Total balance | 37200