## How to use
Awning Install Tracker
A free install tracker for awning installers: schedule installs, assign crews, and track type and status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Track each order from measure to install; Promised turns red when the install date passes.
3 | Commercial awnings may need a sign or encroachment permit; add it before you schedule the crew.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Awning | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-09-13 | Harbor Grill | Storefront fixed awning 20 ft | Scheduled | Crew A | 2026-10-17 | 6800 | 3400 | 3400 | 29
2026-09-23 | Kapoor | Retractable patio 16 x 10 | In fabrication | Crew B | 2026-10-23 | 4300 | 2000 | 2300 | 19
2026-09-29 | Ortiz | Window awnings (4) | Ordered | Crew B | 2026-10-31 | 1900 | 950 | 950 | 13
2026-08-29 | Bloom Florist | Logo awning recover | Installed | Crew A | 2026-10-11 | 2650 | 1300 | 1350
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Installed"),([Stage]="Paid")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Measured | 0
Stage: Ordered | 1
Stage: In fabrication | 1
Stage: Scheduled | 1
Stage: Installed | 1
Stage: Paid | 0
Totals
Total price | 15650
Total deposit | 7650
Total balance | 8000