## How to use
Basement Budget Tracker
A free budget tracker for basement finishing: track budget vs. actual by category with change orders and over-budget flags in Sheets or Excel.
Quick start
1 | Open the Budget tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Every change order gets its own line with an approved price, so the client sees what moved the total.
3 | Variance turns red when a line is over budget; % used turns amber at 90%.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Budget
Category | Line item | Budget | Actual | Status | Variance | % used
Framing | Walls and soffits | 4200 | 4380 | Complete | -180 | 104.3%
Electrical | Circuits, lights, panel tie-in | 5100 | 5100 | Complete | 0 | 100%
Plumbing | Bathroom rough-in | 3600 | 4150 | Complete | -550 | 115.3%
HVAC | Duct extensions | 1800 | 1650 | Complete | 150 | 91.67%
Drywall | Hang and finish | 5400 | 2900 | In progress | 2500 | 53.7%
Flooring | LVP 900 sq ft | 4800 | 0 | Not started | 4800 | 0%
Paint and trim | Paint, doors, base | 3900 | 0 | Not started | 3900 | 0%
Change order | CO-1: wet bar rough-in | 1400 | 1400 | Complete | 0 | 100%

## Summary
Item | Value | Notes
Overview
Entries | 8
By status
Status: Not started | 2
Status: In progress | 1
Status: Complete | 5
Totals
Total budget | 30200
Total actual | 19580
Total variance | 10620