## How to use
Bathroom Remodel Phase Tracker
A free phase tracker for bathroom remodels: track demo, rough-in, tile, and finish phases with subs and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Promised is the target date for the current phase; it turns red when that phase runs late.
3 | Book rough inspections as soon as rough-in is done; they are the usual bottleneck.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Bathroom | Stage | Lead / sub | Promised | Price | Deposit | Balance | Days open
2026-09-25 | Ortiz | Primary bath, full gut | Tile | Rivera Tile | 2026-10-19 | 24500 | 8000 | 16500 | 17
2026-10-03 | Kim | Hall bath refresh | Rough plumbing | Ace Plumbing | 2026-10-27 | 12800 | 4000 | 8800 | 9
2026-09-18 | Brennan | Basement bath (new) | Inspection | City inspector | 2026-10-12 | 18900 | 6000 | 12900 | 24
2026-09-03 | Shah | Powder room | Punch list | In-house | 2026-10-10 | 7400 | 2500 | 4900 | 39
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 1
By stage
Stage: Demo | 0
Stage: Rough plumbing | 1
Stage: Rough electrical | 0
Stage: Inspection | 1
Stage: Tile | 1
Stage: Fixtures | 0
Stage: Punch list | 1
Stage: Complete | 0
Totals
Total price | 63600
Total deposit | 20500
Total balance | 43100