## How to use
Book Launch Planner
A free book launch spreadsheet: plan tasks from pre-order to release with promo and ARC tracking and status for authors, in Google Sheets and Excel.
Quick start
1 | Open the Checklist tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Dates turn red when passed and the task is not Done; work backward from release day.
3 | Collect ARC reviews to post on release day; most stores do not allow reviews before launch.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Checklist
Phase | Task | Owner | Status | Due | Notes
Pre-launch (12 weeks) | Final cover and blurb | Author | Done | 2026-09-01
Pre-launch (12 weeks) | Set up pre-order | Author | Done | 2026-09-15 | All retailers
ARC | Send ARCs to reviewer list | Author | In progress | 2026-10-06 | 40 readers
ARC | Follow up for reviews | VA | Not started | 2026-11-03 | Post on release day
Promo | Book promo site bookings | Author | Waiting | 2026-10-20 | Two sites confirmed
Promo | Newsletter swap with 3 authors | Author | In progress | 2026-10-27
Launch week | Release day email to list | Author | Not started | 2026-11-17
Launch week | Ads: start at $20/day | Author | Not started | 2026-11-17 | Review after 72 hours

## Progress
Item | Value | Notes
Progress
Items | 8
Done | 2
Percent complete | 25%

## Summary
Item | Value | Notes
Overview
Entries | 8
Overdue (due) | 1
By status
Status: Not started | 3
Status: In progress | 2
Status: Waiting | 1
Status: Done | 2
Status: Not needed | 0