## How to use
Cabinet Shop Job Tracker
A free job tracker for cabinet makers: follow jobs from design to install with payments and per-job profit in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Track material and labor cost per job as you go; Profit (Price minus both) is on the job row.
3 | Progress payments: deposit at approval, second payment when building starts, balance at install.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Project | Stage | Lead | Promised | Price | Deposit | Material cost | Labor cost | Balance | Days open | Profit
2026-09-03 | Kapoor | Kitchen: 22 boxes, painted inset | Finishing | Sam | 2026-10-21 | 38500 | 15400 | 11200 | 9800 | 23100 | 39 | 17500
2026-09-18 | Ortiz | Built-in bookcases | Building | Lee | 2026-10-27 | 7800 | 3900 | 1900 | 2600 | 3900 | 24 | 3300
2026-10-03 | Harbor Dental | Reception desk | Materials ordered | Sam | 2026-11-07 | 9400 | 4700 | 2600 | 3100 | 4700 | 9 | 3700
2026-08-04 | Brennan | Vanity and linen tower | Complete | Lee | 2026-10-08 | 6200 | 6200 | 1500 | 2100 | 0 |  | 2600
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Design | 0
Stage: Approved | 0
Stage: Materials ordered | 1
Stage: Building | 1
Stage: Finishing | 1
Stage: Install | 0
Stage: Complete | 1
Totals
Total price | 61900
Total deposit | 30200
Total material cost | 17200
Total labor cost | 17600