## How to use
CAD Drawing Revision Log
A free revision log for CAD drafting: track drawing revisions by number with change notes, dates, and issued-by in Google Sheets or Excel.
Quick start
1 | Open the Revisions tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Add a row for every revision and mark the previous rev Superseded; Issued rows are the current set.
3 | Write change descriptions the field can act on (what moved, where); cloud the change on the drawing too.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Revisions
Drawing # | Title | Rev | Rev date | Change description | Requested by | Drawn by | Checked by | Status | Is current
A-101 | Floor plan, level 1 | A | 2026-09-03 | Initial issue for permit | Client | KD | MS | Superseded | Old
A-101 | Floor plan, level 1 | B | 2026-10-01 | Moved kitchen wall 6 in east | Architect | KD | MS | Issued | Current
A-102 | Floor plan, level 2 | A | 2026-09-03 | Initial issue for permit | Client | KD | MS | Issued | Current
S-201 | Foundation plan | A | 2026-09-13 | Initial issue | Engineer | JL | PE review | Superseded | Old
S-201 | Foundation plan | B | 2026-10-11 | Added footing at grid C4 | Engineer | JL |  | For review | Current

## Register
Item | Value | Notes
Register
Revisions logged | 5
Waiting on review | 1
Current issued sheets | 2