## How to use
Concrete Job Tracker
A free job tracker for concrete contractors: follow jobs from quote to done with payments and per-job profit in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Log material and labor against each job; Profit is price minus both.
3 | Bill the progress payment at the pour and the balance once finished.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Job | Stage | Crew | Promised | Price | Deposit | Material cost | Labor cost | Balance | Days open | Profit
2026-09-29 | Kim | Driveway 24x40, 4 in | Forms and prep | Crew B | 2026-10-16 | 9800 | 3000 | 3150 | 2600 | 6800 | 13 | 4050
2026-10-03 | Lot 15 Oak Meadows | Slab 32 yd | Contract | Crew A | 2026-10-18 | 14200 | 4000 | 5900 | 3800 | 10200 | 9 | 4500
2026-09-23 | Riverside Plaza | Sidewalk 300 ft | Poured | Crew B | 2026-10-14 | 11500 | 3500 | 3900 | 4200 | 8000 | 19 | 3400
2026-09-13 | Ortiz | Patio 20x30 stamped | Paid | Crew A | 2026-10-05 | 8900 | 8900 | 2700 | 2900 | 0 |  | 3300
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Finished"),([Stage]="Paid")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Estimate | 0
Stage: Contract | 1
Stage: Forms and prep | 1
Stage: Poured | 1
Stage: Finished | 0
Stage: Paid | 1
Totals
Total price | 44400
Total deposit | 19400
Total material cost | 15650
Total labor cost | 13500