## How to use
Concrete Pour Schedule
A free pour schedule for concrete contractors: plan pours, crews, and ready-mix orders with weather notes in Sheets or Excel.
Quick start
1 | Open the Pours tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Confirm the ready-mix order the day before and set Ready-mix confirmed to Yes. Forecast lows under 40F turn amber: plan blankets or accelerator.
3 | Keep one row per pour; mark Rained out instead of deleting so you can reschedule.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Pours
Pour date | Start | Job | Pour | Crew | Yards | Mix | Ready-mix confirmed | Pump | Forecast low (F) | Status
2026-10-14 | 7:00 | Lot 14 Oak Meadows | Footings | Crew A | 18 | 3,000 psi | Yes | None | 52 | Inspected
2026-10-14 | 10:30 | Kim residence | Driveway | Crew B | 9 | 4,000 psi air-entrained | No | Line pump | 52 | Planned
2026-10-15 | 6:30 | Lot 15 Oak Meadows | Slab | Crew A | 32 | 3,500 psi fiber | Yes | Boom pump | 38 | Planned
2026-10-17 | 7:00 | Riverside Plaza | Sidewalk | Crew B | 12 | 4,000 psi air-entrained | No | None | 45 | Planned
2026-10-12 | 7:00 | Lot 13 Oak Meadows | Slab | Crew A | 30 | 3,500 psi fiber | Yes | Boom pump | 55 | Poured

## Summary
Item | Value | Notes
Overview
Entries | 5
By status
Status: Planned | 3
Status: Inspected | 1
Status: Poured | 1
Status: Rained out | 0