## How to use
Course Launch Tracker
A free course launch spreadsheet: plan launch tasks by phase, channel, and owner with due-date highlighting for creators, in Google Sheets and Excel.
Quick start
1 | Open the Launch plan tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Work back from cart open; Due turns red for anything late and not done.
3 | Keep the debrief task: conversion by channel is what makes the next launch better.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Launch plan
Due | Task | Phase | Channel | Owner | Status
2026-10-10 | Finalize sales page copy | Pre-launch | Course platform | You | Done
2026-10-15 | Record webinar dry run | Pre-launch | Webinar | You | In progress
2026-10-17 | Schedule 5-email launch sequence | Pre-launch | Email | VA | Not started
2026-10-20 | Live webinar + open cart | Open cart | Webinar | You | Not started
2026-10-21 | Affiliate swipe emails out | Open cart | Affiliates | VA | Not started
2026-10-26 | Cart closing reminders (3) | Close cart | Email | VA | Not started
2026-11-02 | Launch debrief and numbers | Post-launch | Course platform | You | Not started

## Summary
Item | Value | Notes
Overview
Entries | 7
Overdue (due) | 0
By status
Status: Not started | 5
Status: In progress | 1
Status: Done | 1