## How to use
Deck Builder Job Tracker
A free job tracker for deck builders: follow jobs from quote to done with payments and per-job profit in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Log material and labor against each job; Profit is price minus both.
3 | Schedule framing inspections before decking goes down; Promised turns red when a phase runs late.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Deck | Stage | Crew | Promised | Price | Deposit | Material cost | Labor cost | Balance | Days open | Profit
2026-09-18 | Kim | 15x20 composite, 3 ft high | Framing | Crew A | 2026-10-19 | 18600 | 6000 | 7200 | 4400 | 12600 | 24 | 7000
2026-09-28 | Ortiz | 12x16 pressure-treated | Permit | Crew B | 2026-11-02 | 9200 | 3000 | 3100 | 2300 | 6200 | 14 | 3800
2026-09-03 | Harbor HOA | Pool deck resurface | Final inspection | Crew A | 2026-10-15 | 14500 | 7000 | 5900 | 3800 | 7500 | 39 | 4800
2026-08-14 | Shah | 10x12 cedar platform | Paid | Crew B | 2026-09-23 | 6400 | 6400 | 2400 | 1700 | 0 |  | 2300
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Paid")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Estimate | 0
Stage: Contract | 0
Stage: Permit | 1
Stage: Framing | 1
Stage: Decking and rail | 0
Stage: Final inspection | 1
Stage: Paid | 1
Totals
Total price | 48700
Total deposit | 22400
Total material cost | 18600
Total labor cost | 12200