## How to use
Demolition Job Tracker
A free job tracker for demolition contractors: schedule sites, assign crews and machines, and track status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Confirm the asbestos survey and utility disconnects before demolition starts; they gate the schedule.
3 | Promised turns red when a job runs past its finish date.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Equipment | Balance | Days open
2026-09-23 | Harbor Properties | Interior gut, 1,800 sq ft suite | Demolition | Crew A | 2026-10-17 | 9800 | 3000 | Skid steer, 3 roll-offs | 6800 | 19
2026-10-01 | Kim | Detached garage teardown | Utilities off | Crew B | 2026-10-19 | 7400 | 2000 | Mini excavator | 5400 | 11
2026-09-13 | City of Fairview | Old annex (post-abatement) | Haul-off | Crew A | 2026-10-14 | 38500 | 12000 | Excavator 20T, trucks | 26500 | 29
2026-08-29 | Lot 9 Oak Meadows | House demo for rebuild | Complete | Crew B | 2026-10-03 | 16800 | 16800 | Excavator 20T | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Bid | 0
Stage: Survey and permits | 0
Stage: Utilities off | 1
Stage: Demolition | 1
Stage: Haul-off | 1
Stage: Site clean | 0
Stage: Complete | 1
Totals
Total price | 72500
Total deposit | 33800
Total balance | 38700