## How to use
Design Fee Tracker
A free design fee spreadsheet: split contract fee by phase and track billed vs. remaining with add services for architecture firms, in Sheets and Excel.
Quick start
1 | Open the Fees by phase tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Split each project's contract fee by phase (a common split is SD 15%, DD 20%, CD 40%, Bidding 5%, CA 20%).
3 | Update % complete monthly. Ready to bill shows earned fee you haven't invoiced yet (amber).
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Fees by phase
Project | Phase | Phase fee | % complete | Billed to date | Additional services | Reimbursables | Earned | Remaining fee | Ready to bill
Cedar St. residence | Schematic design | 9000 | 100% | 9000 | 0 | 120 | 9000 | 0 | 0
Cedar St. residence | Design development | 12000 | 60% | 6000 | 1500 | 85 | 8700 | 7500 | 2700
Cedar St. residence | Construction documents | 24000 | 0% | 0 | 0 | 0 | 0 | 24000 | 0
Harbor clinic TI | Construction documents | 18500 | 85% | 12000 | 0 | 340 | 15725 | 6500 | 3725
Harbor clinic TI | Construction admin | 9500 | 20% | 0 | 0 | 0 | 1900 | 9500 | 1900
Elm Library addition | Bidding | 4200 | 50% | 4200 | 0 | 60 | 2100 | 0 | 0

## Fee summary
Item | Value | Notes
Total contract fees | 78700
Billed to date | 31200
Earned not yet billed | 8325 | Bill this at your next invoice cycle.
Fee remaining | 47500
Reimbursables to invoice | 605