## How to use
Interior Design Project Tracker
A free interior design project spreadsheet: track phase, deadlines, and status room by room across projects, in Google Sheets and Excel.
Quick start
1 | Open the Projects tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Track each room as its own row with the next milestone and its due date. Due date turns red when it passes and the row isn't Done.
3 | Filter Status = Waiting on client before client calls; the Summary tab counts rooms by status.
4 | Due date turns red once the date has passed and Status is not Done.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Projects
Project | Client | Room | Phase | Next milestone | Due date | Status | Notes
Lake house refresh | The Parkers | Great room | Procurement | Sofa delivery | 2026-10-19 | On track | Track RH shipment
Lake house refresh | The Parkers | Kitchen | Design development | Tile selection meeting | 2026-10-11 | Waiting on client
Office suite | Dr. Amara Cole | Reception | Installation | Art hanging | 2026-10-14 | At risk | Installer availability
Primary suite | M. Lindqvist | Bedroom | Concept | Mood board presentation | 2026-10-22 | On track
Salon buildout | Wren & Co. | Styling floor | Complete | Final walkthrough | 2026-10-01 | Done | Punch list closed

## Summary
Item | Value | Notes
Overview
Entries | 5
Overdue (due date) | 1
By status
Status: On track | 2
Status: At risk | 1
Status: Waiting on client | 1
Status: Done | 1