## How to use
Dock Build Tracker
A free build tracker for dock builders: track permits, crew, and install status by job in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Waterfront permits (local, state, sometimes Army Corps) take longest: track the submission date closely.
3 | Promised turns red when a phase runs late; water levels and seasonal restrictions can move dates.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope / waterway | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-08-14 | Hale | 40 ft walkway + platform, lake | Pilings | Barge crew | 2026-11-02 | 38500 | 12000 | 26500 | 59
2026-08-29 | Ortiz | Floating dock 8x24, river | Permit approved | Crew B | 2026-10-27 | 14200 | 5000 | 9200 | 44
2026-09-13 | Lakeside HOA | Community dock repair | Permit submitted | Barge crew | 2026-11-27 | 22000 | 6000 | 16000 | 29
2026-07-15 | Kim | Boat lift install | Complete | Crew B | 2026-09-28 | 8600 | 8600 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Estimate | 0
Stage: Permit submitted | 1
Stage: Permit approved | 1
Stage: Pilings | 1
Stage: Framing and decking | 0
Stage: Lift install | 0
Stage: Complete | 1
Totals
Total price | 83300
Total deposit | 31600
Total balance | 51700