## How to use
Drywall Job Tracker
A free job tracker for drywall contractors: track hang, tape, and finish phases with crew and status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Promised is the finish date for the current phase; mud needs dry time between coats, so leave a day.
3 | Board square footage helps compare price per square foot across jobs.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Address / scope | Stage | Crew | Promised | Price | Deposit | Board (sq ft) | Balance | Days open
2026-10-07 | Rivera Builders | Lot 14 Oak Meadows: whole house | Mud coats | Crew A | 2026-10-16 | 14800 | 4000 | 7200 | 10800 | 5
2026-10-10 | Kim | Basement finish | Hang | Crew B | 2026-10-19 | 6900 | 2000 | 2400 | 4900 | 2
2026-10-12 | Harbor Dental | Suite TI walls | Scheduled | Crew B | 2026-10-21 | 5200 | 0 | 1800 | 5200 | 0
2026-10-01 | Ortiz | Garage conversion | Complete | Crew A | 2026-10-11 | 3400 | 3400 | 1100 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Scheduled | 1
Stage: Hang | 1
Stage: Tape | 0
Stage: Mud coats | 1
Stage: Sand and prime | 0
Stage: Complete | 1
Totals
Total price | 30300
Total deposit | 9400
Total balance | 20900