## How to use
Excavation Job Tracker
A free job tracker for excavation contractors: schedule sites, assign crews and machines, and track status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Call 811 and wait for locates before any digging; the job sits in that stage until marks are in.
3 | Promised turns red when a phase runs late; weather days are worth noting in the scope.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Equipment | Cubic yards | Balance | Days open
2026-10-03 | Rivera Builders | Basement dig, Lot 15 | Excavation | Crew A | 2026-10-15 | 18400 | 6000 | Excavator 20T, 2 trucks | 710 | 12400 | 9
2026-10-07 | Kim | Septic field | 811 locates | Crew B | 2026-10-21 | 9600 | 3000 | Mini excavator | 120 | 6600 | 5
2026-10-10 | Harbor HOA | Drainage swale regrade | Bid | Crew B | 2026-10-28 | 6200 | 0 | Skid steer | 60 | 6200 | 2
2026-09-18 | Ortiz | Pool dig | Complete | Crew A | 2026-10-07 | 12800 | 12800 | Excavator 20T | 340 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Bid | 1
Stage: 811 locates | 1
Stage: Excavation | 1
Stage: Backfill and compaction | 0
Stage: Grading | 0
Stage: Complete | 1
Totals
Total price | 47000
Total deposit | 21800
Total balance | 25200