## How to use
Fabrication Job Tracker
A free fabrication job spreadsheet: track jobs from quote to delivery by scope, stage, and due date with a workload view in Google Sheets and Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Promised dates turn red when passed unless the job is Ready or Delivered.
3 | Shop hours by job help you see how many weeks of work are booked.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Job | Stage | Lead | Promised | Price | Deposit | Shop hours est. | Balance | Days open
2026-09-23 | Hill Street condos | Stair railing, 3 flights | Fabrication | Marco | 2026-10-17 | 8400 | 4200 | 60 | 4200 | 19
2026-09-28 | Brewster Farm | Gate and posts | Finishing | Leo | 2026-10-12 | 2600 | 1300 | 18 | 1300 | 14
2026-10-03 | City parks | Bike racks (12) | Material ordered | Marco | 2026-10-27 | 5400 | 0 | 30 | 5400 | 9
2026-10-09 | Ortiz residence | Spiral stair | Approved | Leo | 2026-11-12 | 14800 | 7400 | 110 | 7400 | 3
2026-09-13 | Diner on 5th | Hood frame | Delivered | Marco | 2026-10-03 | 1900 | 1900 | 12 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Ready"),([Stage]="Delivered")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 5
Overdue (promised) | 0
By stage
Stage: Quoted | 0
Stage: Approved | 1
Stage: Material ordered | 1
Stage: Fabrication | 1
Stage: Finishing | 1
Stage: Ready | 0
Stage: Delivered | 1
Totals
Total price | 33100
Total deposit | 14800
Total balance | 18300
Total shop hours est. | 230