## How to use
Facility Work Order Log
A free work order log for facility management: track work by asset and priority with assigned techs and cost in Google Sheets or Excel.
Quick start
1 | Open the Work orders tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Target date comes from priority (same day, 2 days, 7 days, 30 days); late open orders turn red. Edit the targets in the formula to your SLAs.
3 | Track cost and downtime by asset to spot equipment that is due for replacement.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Work orders
WO # | Opened | Building | Asset | Issue | Priority | Assigned to | Status | Labor cost | Parts and vendor cost | Downtime hours | Target date | Total cost
WO-3301 | 2026-10-08 | HQ | RTU-2 rooftop unit | Not cooling | High | Coolair HVAC (vendor) | Waiting on parts | 180 | 640 | 0 | 2026-10-10 | 820
WO-3304 | 2026-10-10 | HQ | Restroom 2F | Running toilet | Normal | Sam | Complete | 45 | 18 | 0 | 2026-10-17 | 63
WO-3307 | 2026-10-12 | Warehouse | Dock door 3 | Will not close | Emergency | Door Pros (vendor) | Vendor scheduled | 0 | 0 | 14 | 2026-10-12 | 0
WO-3309 | 2026-10-13 | HQ | Lobby lights | Two fixtures out | Low | Sam | Open | 0 | 0 | 0 | 2026-11-12 | 0
Formulas:
Target date = IF([WO #]="","",IF(([Priority]="Emergency"),[Opened],IF(([Priority]="High"),([Opened]+2),IF(([Priority]="Normal"),([Opened]+7),([Opened]+30)))))

## Status
Item | Value | Notes
Open
Open work orders | 3
Emergency or high open | 2
Cost
Cost this period | 883
Downtime hours | 14