## How to use
Foundation Job Tracker
A free job tracker for foundation repair pros: schedule jobs, assign crews, and track scope and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Get the engineer's letter and permit before installing; Promised turns red when a phase slips.
3 | Many buyers and lenders want the final engineer's letter, so keep it in the job file.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Piers | Balance | Days open
2026-09-23 | Holt | Rear wall settlement | Install piers | Crew A | 2026-10-15 | 9800 | 4900 | 8 | 4900 | 19
2026-10-01 | Sato | Bowing wall anchors | Permit | Crew B | 2026-10-23 | 6400 | 3200 | 4 | 3200 | 11
2026-10-07 | Kline | Corner settlement | Engineer letter | Crew A | 2026-10-31 | 5200 | 0 | 5 | 5200 | 5
2026-09-03 | Parker | Crawlspace support posts | Complete | Crew B | 2026-10-01 | 4800 | 4800 | 6 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Inspection | 0
Stage: Engineer letter | 1
Stage: Permit | 1
Stage: Install piers | 1
Stage: Backfill and cleanup | 0
Stage: Final letter | 0
Stage: Complete | 1
Totals
Total price | 26200
Total deposit | 12900
Total balance | 13300