## How to use
Furniture Build Tracker
A free build tracker for furniture makers: move commissions through mill, joinery, and finish with hours logged in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Hours logged against quoted hours shows whether each build is on budget.
3 | Promised dates turn red when passed and the piece is not delivered; finishing time is often underestimated.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Piece | Stage | Maker | Promised | Price | Deposit | Quoted hours | Hours logged | Balance | Days open
2026-09-03 | Morgan family | Walnut dining table | Finish | Sam | 2026-10-18 | 6800 | 3400 | 60 | 52 | 3400 | 39
2026-09-23 | K. Shaw | Cherry bookcase | Joinery | Sam | 2026-10-31 | 3200 | 1600 | 35 | 14 | 1600 | 19
2026-10-03 | Harbor Inn | Oak benches x 4 | Milling | Ana | 2026-11-12 | 4400 | 2200 | 48 | 6 | 2200 | 9
2026-08-14 | L. Ito | Maple nightstands (pair) | Delivered | Ana | 2026-10-01 | 2400 | 2400 | 30 | 33 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Delivered")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Design | 0
Stage: Lumber | 0
Stage: Milling | 1
Stage: Joinery | 1
Stage: Glue-up | 0
Stage: Finish | 1
Stage: Delivered | 1
Totals
Total price | 16800
Total deposit | 9600
Total balance | 7200
Total quoted hours | 173
Total hours logged | 105