## How to use
Genealogy Client Project Tracker
A free project tracker for professional genealogists: track client research by scope with hours against retainer in Google Sheets or Excel.
Quick start
1 | Open the Projects tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Log research hours against the retainer; Hours left turns amber near the end so you can ask before going over.
3 | Report due turns red if a report is late; cite every source in the report itself.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Projects
Client | Scope | Retainer hours | Hours logged | Hourly rate | Stage | Report due | Hours left | Billed
Hale family | Irish immigrant ancestor, 1850s Boston | 20 | 14.5 | 65 | Analysis | 2026-10-25 | 5.5 | 942.5
M. Ortiz | Lineage society application (DAR) | 15 | 15.5 | 65 | Report writing | 2026-10-16 | -0.5 | 1007.5
K. Brooks | Adoptee DNA match analysis | 10 | 3 | 75 | Records search | 2026-11-07 | 7 | 225
J. Patel | House history, 1890 farmhouse | 8 | 8 | 60 | Delivered | 2026-10-08 | 0 | 480

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (report due) | 0
By stage
Stage: Intake | 0
Stage: Records search | 1
Stage: Analysis | 1
Stage: Report writing | 1
Stage: Delivered | 1
Totals
Total billed | 2655
Total retainer hours | 53
Total hours logged | 41