## How to use
Glass Fabrication Job Tracker
A free job tracker for glass fabrication shops: move jobs through cut, edge, temper, and delivery with due dates in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Promised dates turn red when the job is not installed; tempered glass cannot be recut, so measure twice.
3 | Track tempering pickup dates from your supplier; they set the install date.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Job | Stage | Installer | Promised | Price | Deposit | Type | Balance | Days open
2026-10-01 | Ortiz bathroom | Frameless shower | Tempering (out) | Marco | 2026-10-17 | 2850 | 1425 | Shower | 1425 | 11
2026-10-05 | Harbor Inn | Lobby mirrors x 4 | Edgework | Ana | 2026-10-19 | 1900 | 950 | Mirror | 950 | 7
2026-10-08 | Bistro 21 | Table tops x 12 | Ordered / cut | Marco | 2026-10-25 | 3100 | 1550 | Table top | 1550 | 4
2026-09-23 | K. Shaw | Window reglaze | Installed | Ana | 2026-10-06 | 640 | 640 | Window | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Installed")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Measured | 0
Stage: Ordered / cut | 1
Stage: Edgework | 1
Stage: Tempering (out) | 1
Stage: Ready to install | 0
Stage: Installed | 1
Totals
Total price | 8490
Total deposit | 4565
Total balance | 3925