## How to use
Hardscape Job Tracker
A free job tracker for hardscaping contractors: schedule jobs, assign crews, and track material delivery in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Order material when the contract is signed; Material delivery shows what is on site before excavation.
3 | Walls over about 4 ft usually need an engineered design and permit.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Material delivery | Balance | Days open
2026-09-23 | Kim | Paver patio 400 sq ft + fire pit | Base and compaction | Crew A | 2026-10-17 | 16800 | 5000 | Delivered | 11800 | 19
2026-09-29 | Ortiz | Retaining wall 60 ft, 3 ft high | Excavation | Crew B | 2026-10-23 | 12400 | 4000 | Ordered | 8400 | 13
2026-10-05 | Harbor HOA | Walkway replacement | Contract | Crew B | 2026-11-07 | 9600 | 3000 | Not ordered | 6600 | 7
2026-09-03 | Lee | Driveway pavers 800 sq ft | Complete | Crew A | 2026-10-04 | 21500 | 21500 | Delivered | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Design | 0
Stage: Contract | 1
Stage: Excavation | 1
Stage: Base and compaction | 1
Stage: Pavers / walls | 0
Stage: Cleanup | 0
Stage: Complete | 1
Totals
Total price | 60300
Total deposit | 33500
Total balance | 26800