## How to use
HOA Maintenance Request Log
A free maintenance request log for HOAs: track common-area requests by area with assigned vendors and status in Google Sheets or Excel.
Quick start
1 | Open the Requests tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Log every request with a priority and a target date; Urgent items are highlighted, and Target date turns red if it passes before the request is Done.
3 | Record the vendor estimate and actual cost so the board can compare. The Summary tab totals spend.
4 | Target date turns red once the date has passed and Status is not Done.
5 | The Summary tab keeps running totals and counts. It updates as you add rows.
6 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Requests
Date reported | Area | Issue | Reported by | Priority | Vendor | Est. cost | Actual cost | Target date | Status
2026-10-04 | Pool | Pump motor tripping breaker | Unit 214 | Urgent | BlueWave Pools | 650 | 712 | 2026-10-07 | Done
2026-10-07 | Landscaping | Dead shrubs at front entrance | Board | Low | GreenScape | 420 |  | 2026-10-21 | Scheduled
2026-10-09 | Gate & access | Keypad not reading fobs | Unit 108 | High | SecureGate | 300 |  | 2026-10-12 | Open
2026-10-10 | Parking | Restripe visitor spaces | Board | Medium | StripeRight | 980 |  | 2026-11-02 | Scheduled
2026-10-12 | Clubhouse | Leak under kitchenette sink | Manager | High | Ace Plumbing | 180 |  | 2026-10-15 | Open

## Summary
Item | Value | Notes
Overview
Entries | 5
Overdue (target date) | 0
By status
Status: Open | 2
Status: Scheduled | 2
Status: Done | 1
Totals
Total est. cost | 2530
Total actual cost | 712