## How to use
Home Build Budget Tracker
A free build budget tracker for home builders: track cost codes, budget vs. actual, and variance with overage flags in Sheets or Excel.
Quick start
1 | Open the Cost codes tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Committed is signed POs and subcontracts; Variance compares budget with the higher of committed or paid.
3 | Allowance overages are the buyer's upgrades: bill them as change orders, not your loss.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Cost codes
Cost code | Description | Type | Budget | Committed | Actual paid | Variance | % of budget
01-100 | Permits and fees | Fixed | 14500 | 14500 | 14500 | 0 | 100%
03-300 | Foundation | Fixed | 38000 | 39800 | 39800 | -1800 | 104.7%
06-100 | Framing labor and lumber | Fixed | 92000 | 88500 | 61000 | 3500 | 96.2%
08-500 | Windows and doors | Fixed | 31000 | 30200 | 15100 | 800 | 97.42%
09-600 | Flooring | Allowance | 22000 | 25400 | 0 | -3400 | 115.5%
11-400 | Appliances | Allowance | 12000 | 10800 | 0 | 1200 | 90%
22-000 | Plumbing | Fixed | 28000 | 28000 | 14000 | 0 | 100%
99-000 | Contingency | Fixed | 20000 | 0 | 0 | 20000 | 0%

## Project
Item | Value | Notes
Project
Contract price | 289000 | Contract price for the cost codes listed (sample covers part of a build).
Total budget | 257500
Total committed | 237200
Allowance overage | 2200 | Usually billed to the buyer as a change order.
Projected margin | 31800

## Summary
Item | Value | Notes
Overview
Entries | 8
Totals
Total budget | 257500
Total committed | 237200
Total actual paid | 144400
Total variance | 20300