## How to use
Construction Schedule
A free construction schedule for home builders: sequence phases, tasks, and trades with critical-path highlighting in Sheets or Excel.
Quick start
1 | Open the Schedule tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Give every task an ID and list what it depends on. Start dates should follow the finish of those tasks.
3 | Enter float (days of slack) from your planning. Zero-float tasks are marked Critical; Finish turns red when a task runs past its date unfinished.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Schedule
ID | Phase | Task | Trade | Depends on | Start | Duration (days) | Float (days) | Status | Finish | Critical
T1 | Site prep | Clear lot and rough grade | Excavation – Delgado |  | 2026-09-13 | 4 | 0 | Done | 2026-09-16 | Critical
T2 | Foundation | Footings and slab pour | Concrete – Ridgeline | T1 | 2026-09-18 | 8 | 0 | Done | 2026-09-25 | Critical
T3 | Framing | Frame walls, roof trusses, sheathing | Framing – Hollis | T2 | 2026-09-27 | 15 | 0 | In progress | 2026-10-11 | Critical
T4 | Framing | Windows and exterior doors | Hollis | T3 | 2026-10-12 | 3 | 2 | Not started | 2026-10-14
T5 | Rough-ins | Plumbing rough-in | Ace Plumbing | T3 | 2026-10-14 | 4 | 0 | Not started | 2026-10-17 | Critical
T6 | Rough-ins | Electrical rough-in | Bright Electric | T3 | 2026-10-14 | 5 | 0 | Not started | 2026-10-18 | Critical
T7 | Rough-ins | HVAC rough-in | Comfort Air | T3 | 2026-10-15 | 4 | 1 | Not started | 2026-10-18
T8 | Insulation & drywall | Insulation and drywall hang/finish | Drywall – Pro Finish | T5, T6, T7 | 2026-10-21 | 12 | 0 | Not started | 2026-11-01 | Critical
Formulas:
Finish = IF([ID]="","",(([Start]+[Duration (days)])-1))