## How to use
Home Theater Install Tracker
A free install tracker for home theater pros: track pre-wire, trim, and final phases with tech and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | New construction: pre-wire before drywall, trim-out after paint. Promised turns red when a phase slips.
3 | Schedule a final walkthrough to teach the remote; it saves service calls.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Room / gear | Stage | Tech | Promised | Price | Deposit | Balance | Days open
2026-09-13 | Patel | Basement 7.2.4 Atmos, 120 in screen | Trim-out | Rob | 2026-10-23 | 24800 | 12400 | 12400 | 29
2026-10-01 | Hale | Living room 5.1 + TV mount | Equipment install | Ana | 2026-10-15 | 6900 | 3450 | 3450 | 11
2026-10-05 | Rivera Builders Lot 14 | Whole-house pre-wire | Pre-wire | Rob | 2026-10-18 | 4200 | 2100 | 2100 | 7
2026-08-29 | Kim | Media room 5.1.2 | Complete | Ana | 2026-10-01 | 14500 | 14500 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Design | 0
Stage: Pre-wire | 1
Stage: Trim-out | 1
Stage: Equipment install | 1
Stage: Programming | 0
Stage: Final walkthrough | 0
Stage: Complete | 1
Totals
Total price | 50400
Total deposit | 32450
Total balance | 17950