## How to use
Insulation Job Tracker
A free job tracker for insulation contractors: schedule jobs, assign crews, and track type and status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Air seal before insulating; a blower-door test at Final test shows the improvement for rebates.
3 | Promised turns red when a job slips past its date.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Type / area | Stage | Crew | Promised | Price | Deposit | Sq ft | Balance | Days open
2026-10-03 | Holt | Attic blown cellulose R-49 | Scheduled | Crew A | 2026-10-16 | 2850 | 900 | 1200 | 1950 | 9
2026-10-07 | Sato | Crawlspace encapsulation | Contract | Crew B | 2026-10-25 | 6400 | 2000 | 900 | 4400 | 5
2026-10-10 | Rivera Builders Lot 14 | Spray foam walls (new build) | Assessment | Crew B | 2026-10-22 | 9800 | 0 | 2600 | 9800 | 2
2026-09-23 | Kline | Attic air seal + R-60 | Complete | Crew A | 2026-10-05 | 3400 | 3400 | 1100 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Assessment | 1
Stage: Contract | 1
Stage: Scheduled | 1
Stage: Air sealing | 0
Stage: Insulation installed | 0
Stage: Final test | 0
Stage: Complete | 1
Totals
Total price | 22450
Total deposit | 6300
Total balance | 16150