## How to use
Kitchen Remodel Phase Tracker
A free phase tracker for kitchen remodels: track demo, rough-in, cabinet, and finish phases with subs and status in Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Countertop template happens after cabinets are installed; fabrication takes 1 to 2 weeks, so plan backsplash after.
3 | Promised is the target for the current phase; it turns red when that phase runs late.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Kitchen | Stage | Lead / sub | Promised | Price | Deposit | Balance | Days open
2026-09-13 | Kapoor | Full remodel, 12x15 | Countertop template | Stone Works | 2026-10-16 | 58000 | 23000 | 35000 | 29
2026-09-29 | Brooks | Cabinet refresh + quartz | Cabinets | In-house | 2026-10-18 | 26500 | 10000 | 16500 | 13
2026-09-22 | Ortiz | Galley remodel | Inspection | City inspector | 2026-10-12 | 34000 | 12000 | 22000 | 20
2026-08-14 | Shah | Full remodel | Punch list | In-house | 2026-10-11 | 61000 | 50000 | 11000 | 59
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 1
By stage
Stage: Demo | 0
Stage: Rough-ins | 0
Stage: Inspection | 1
Stage: Drywall | 0
Stage: Cabinets | 1
Stage: Countertop template | 1
Stage: Countertops | 0
Stage: Backsplash and trim | 0
Totals
Total price | 179500
Total deposit | 95000
Total balance | 84500