## How to use
Land Development Project Budget
A free project budget for land developers: compare budget vs. actual by category and phase with over-budget flags in Sheets or Excel.
Quick start
1 | Open the Budget tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Tag every budget line with phase and cost type (land, soft, hard), then post actuals from pay applications and invoices.
3 | Remaining turns red per line when over budget; the Roll-up tab totals by cost type and phase for lender draws.
4 | Enter Budget once, then update Actual as money goes out. Remaining turns red when a line is over budget.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Budget
Phase | Cost type | Category | Budget | Actual | Vendor | Remaining | % used
All phases | Land | Land acquisition (42 ac) | 1260000 | 1260000 | Seller – Harlan Trust | 0 | 100%
All phases | Soft | Engineering and platting | 185000 | 142500 | Meridian Civil | 42500 | 77.03%
All phases | Soft | Entitlements and permits | 64000 | 58200 | County | 5800 | 90.94%
Phase 1 | Hard | Clearing and mass grading | 310000 | 296000 | Delgado Excavation | 14000 | 95.48%
Phase 1 | Hard | Water, sewer and storm | 640000 | 512000 | Ridgeline Utilities | 128000 | 80%
Phase 1 | Hard | Paving and curb | 420000 | 0 | Apex Paving | 420000 | 0%
Phase 2 | Hard | Clearing and grading | 270000 | 0 |  | 270000 | 0%

## Roll-up
Item | Value | Notes
By cost type
Land – budget | 1260000
Land – actual | 1260000
Soft – budget | 249000
Soft – actual | 200700
Hard – budget | 1640000
Hard – actual | 808000
By phase
Phase 1 – budget | 1370000
Phase 1 – actual | 808000
Phase 2 – budget | 270000
Phase 2 – actual | 0
Project
Total budget | 3149000
Total spent | 2268700
Remaining | 880300