## How to use
Masonry Job Tracker
A free job tracker for masonry contractors: schedule jobs, assign crews, and track type and status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Mortar needs temperatures above about 40F to cure; weather can move start dates.
3 | Promised turns red when a job runs late.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Type / area | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-09-29 | Holt | Chimney rebuild above roofline | In progress | Crew A | 2026-10-16 | 6800 | 3400 | 3400 | 13
2026-10-04 | Harbor Grill | Brick storefront repointing | Contract | Crew B | 2026-10-27 | 9400 | 3000 | 6400 | 8
2026-10-08 | Ortiz | Stone veneer, front porch | Material delivered | Crew A | 2026-10-21 | 7200 | 3600 | 3600 | 4
2026-09-13 | Kim | Block retaining wall | Complete | Crew B | 2026-10-07 | 11800 | 11800 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Estimate | 0
Stage: Contract | 1
Stage: Material delivered | 1
Stage: In progress | 1
Stage: Cure and cleanup | 0
Stage: Complete | 1
Totals
Total price | 35200
Total deposit | 21800
Total balance | 13400