## How to use
Meeting Action Item Tracker
A free meeting action spreadsheet: capture action items by owner and due date with status so nothing from a meeting slips, in Sheets and Excel.
Quick start
1 | Open the Actions tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Capture every action with an owner and due date before the meeting ends; review open items at the start of the next one.
3 | Overdue items turn red and items open more than 14 days amber.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Actions
Meeting date | Meeting | Action item | Owner | Due | Status | Notes | Days open
2026-09-29 | Weekly ops | Update vendor contact list | Sam | 2026-10-06 | Done
2026-09-29 | Weekly ops | Get 3 quotes for new copier | Ana | 2026-10-09 | In progress | 2 of 3 received | 13
2026-10-06 | Weekly ops | Fix door badge reader | Leo | 2026-10-11 | Blocked | Waiting on vendor | 6
2026-10-06 | Quarterly planning | Draft Q1 hiring plan | Dana | 2026-10-20 | Open |  | 6
2026-10-13 | Weekly ops | Book holiday party venue | Priya | 2026-10-23 | Open |  | -1
Formulas:
Days open = IF([Meeting date]="","",IF(OR(([Status]="Done"),([Status]="Dropped")),"",(TODAY()-[Meeting date])))

## Status
Item | Value | Notes
Status
Open items | 4
Overdue | 2
Blocked | 1