## How to use
App Feature & Sprint Tracker
A free feature and sprint tracker for mobile app agencies: track features by sprint with estimates and status in Google Sheets or Excel.
Quick start
1 | Open the Backlog tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Keep must-haves in the current sprint and estimate in points; compare points per sprint with your team's velocity.
3 | Due turns red for late items; blocked items need a decision from the client or another team.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Backlog
Feature | Project | Sprint | Priority | Estimate (points) | Owner | Status | Due
Login with Apple / Google | Peak Fitness app | Sprint 7 | Must | 5 | Ana | In review | 2026-10-15
Class booking screen | Peak Fitness app | Sprint 7 | Must | 8 | Ben | In progress | 2026-10-17
Push reminders | Peak Fitness app | Sprint 8 | Should | 5 | Ana | In sprint | 2026-10-27
Apple Health sync | Peak Fitness app | Sprint 9 | Could | 8 |  | Backlog | 2026-11-10
Order history | Bloom Florist app | Sprint 3 | Must | 3 | Ben | Blocked | 2026-10-12

## Sprint
Item | Value | Notes
Capacity
Points in Sprint 7 | 13
Points done | 0
Risks
Blocked items | 1