## How to use
Painting Job Tracker
A free painting job tracker spreadsheet: move jobs from lead to paid with value, crew, and schedule for painting contractors, in Sheets and Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Move leads through to paid; Promised turns red when a job or follow-up is late.
3 | Exterior work depends on weather: note rain days so customers know why dates moved.
4 | Mark Stage as "Paid" when money arrives; the Summary tab splits price into collected and outstanding.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Scope | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-09-29 | Vance | Exterior, 2-story colonial | Prep | Crew A | 2026-10-18 | 7800 | 2600 | 5200 | 13
2026-10-04 | Kapoor | Interior: 4 rooms + trim | Booked | Crew B | 2026-10-21 | 4200 | 1400 | 2800 | 8
2026-10-09 | Harbor Dental | Office repaint, after hours | Estimate sent | Crew B | 2026-11-02 | 6900 | 0 | 6900 | 3
2026-10-11 | Lee | Cabinet refinishing | Lead |  | 2026-10-18 | 0 | 0 | 0 | 1
2026-09-13 | Ortiz | Exterior trim and doors | Paid | Crew A | 2026-10-03 | 3100 | 3100 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Paid")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 5
Overdue (promised) | 0
By stage
Stage: Lead | 1
Stage: Estimate sent | 1
Stage: Booked | 1
Stage: Prep | 1
Stage: Painting | 0
Stage: Walkthrough | 0
Stage: Paid | 1
Totals
Total price | 22000
Total deposit | 7100
Total balance | 14900
Collected | 3100
Outstanding | 18900