## How to use
Patent Search Project Tracker
A free project tracker for patent search services: move searches from scope to report with hours and due dates in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Agree on scope and a hours budget up front; Hours logged near the budget means a check-in with the client.
3 | Promised turns red when a report is late; search reports are not legal opinions.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Search type | Stage | Searcher | Promised | Price | Deposit | Hours budget | Hours logged | Balance | Days open
2026-10-01 | Klein & Moss (client: Westline) | Freedom-to-operate: pump assembly | Analysis | R. Shah | 2026-10-18 | 4800 | 2400 | 24 | 19 | 2400 | 11
2026-10-05 | Inventor: D. Ito | Patentability: folding bike hinge | Searching | M. Chen | 2026-10-20 | 1500 | 750 | 10 | 4 | 750 | 7
2026-10-08 | Lumen Labs | Invalidity: competitor patent | Scoping | R. Shah | 2026-11-02 | 6500 | 3250 | 32 | 2 | 3250 | 4
2026-09-18 | Atlas Retail | Landscape: smart lockers | Delivered | M. Chen | 2026-10-10 | 3200 | 3200 | 16 | 17 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Delivered")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Scoping | 1
Stage: Searching | 1
Stage: Analysis | 1
Stage: Report draft | 0
Stage: Delivered | 1
Totals
Total price | 16000
Total deposit | 9600
Total balance | 6400
Total hours budget | 82
Total hours logged | 42