## How to use
Paving Job Tracker
A free job tracker for paving contractors: schedule jobs, assign crews, and track type and status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Paving needs dry weather and warm ground (about 50F and rising); Promised turns red when a job slips.
3 | Sealcoat new asphalt only after it cures (often 6 to 12 months).
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Type / area | Stage | Crew | Promised | Price | Deposit | Sq ft | Balance | Days open
2026-10-03 | Mendez | Driveway replacement, asphalt | Prep and base | Crew A | 2026-10-16 | 7400 | 2500 | 1100 | 4900 | 9
2026-10-07 | Harbor Plaza | Parking lot overlay | Contract | Crew B | 2026-10-27 | 38500 | 10000 | 18000 | 28500 | 5
2026-10-10 | Fairview Church | Sealcoat + restripe | Estimate | Crew B | 2026-11-02 | 4600 | 0 | 22000 | 4600 | 2
2026-09-23 | Kim | Driveway extension | Complete | Crew A | 2026-10-05 | 3200 | 3200 | 400 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Estimate | 1
Stage: Contract | 1
Stage: Prep and base | 1
Stage: Paving | 0
Stage: Sealcoat / striping | 0
Stage: Complete | 1
Totals
Total price | 53700
Total deposit | 15700
Total balance | 38000