## How to use
Pergola Build Tracker
A free build tracker for pergola builders: schedule jobs, assign crews, and track scope and status in Google Sheets or Excel.
Quick start
1 | Open the Jobs tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Footings need inspection in many towns before framing; Promised turns red when a phase slips.
3 | Attached pergolas tie into the house, which usually means a permit even when freestanding ones do not.
4 | The Summary tab keeps running totals and counts. It updates as you add rows.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Jobs
Opened | Customer | Design / size | Stage | Crew | Promised | Price | Deposit | Balance | Days open
2026-09-25 | Patel | 12x14 cedar, freestanding | Framing | Crew A | 2026-10-16 | 7900 | 3950 | 3950 | 17
2026-10-03 | Ortiz | Attached aluminum, louvered | Permit | Crew B | 2026-10-27 | 14500 | 7250 | 7250 | 9
2026-10-09 | Harbor Grill | Patio pergola with shade sails | Design | Crew A | 2026-11-07 | 11200 | 0 | 11200 | 3
2026-09-13 | Kim | 10x10 cedar kit install | Complete | Crew B | 2026-10-06 | 3400 | 3400 | 0
Formulas:
Days open = IF([Opened]="","",IF(OR(([Stage]="Complete")),"",(TODAY()-[Opened])))

## Summary
Item | Value | Notes
Overview
Entries | 4
Overdue (promised) | 0
By stage
Stage: Design | 1
Stage: Permit | 1
Stage: Footings | 0
Stage: Framing | 1
Stage: Finish (stain / roof) | 0
Stage: Complete | 1
Totals
Total price | 37000
Total deposit | 14600
Total balance | 22400