## How to use
Podcast Launch Checklist
A free podcast launch checklist spreadsheet: every pre-launch task by phase with owners and due dates to start a show, in Google Sheets and Excel.
Quick start
1 | Open the Checklist tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Due dates turn red when passed and the task is not done; directory approval takes time, so submit early.
3 | Use only music and clips you have the rights to.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Checklist
Phase | Task | Owner | Status | Due | Show | Notes
Concept | Define show format and episode length | Host | Done | 2026-09-13 | The Small Shop Show
Branding | Cover art 3000 x 3000 | Designer | Done | 2026-09-29 | The Small Shop Show | Check legibility at thumbnail size
Branding | Intro and outro music (licensed) | Host | In progress | 2026-10-11 | The Small Shop Show | Keep the license
Production | Record 3 launch episodes | Host | In progress | 2026-10-18 | The Small Shop Show
Production | Edit and master to -16 LUFS | Editor | Not started | 2026-10-23 | The Small Shop Show
Distribution | Set up hosting and RSS feed | Host | Not started | 2026-10-20 | The Small Shop Show
Distribution | Submit to Apple Podcasts and Spotify | Host | Not started | 2026-10-25 | The Small Shop Show | Approval can take days
Launch | Launch email and social posts | Host | Not started | 2026-11-03 | The Small Shop Show
Launch | Ask 10 friends to rate and review | Host | Not started | 2026-11-04 | The Small Shop Show

## Progress
Item | Value | Notes
Progress
Items | 9
Done | 2
Percent complete | 22.22%

## Summary
Item | Value | Notes
Overview
Entries | 9
Overdue (due) | 1
By status
Status: Not started | 5
Status: In progress | 2
Status: Done | 2
Status: Not needed | 0