## How to use
Pool Build Phase Tracker
A free phase tracker for pool builders: track dig, steel, plumbing, and plaster phases with crew and status in Sheets or Excel.
Quick start
1 | Open the Phases tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Add a row per phase per job with the crew or sub and target dates. Target finish turns red when a phase runs late.
3 | Log inspections and their results; failed inspections are highlighted so re-inspections get scheduled.
4 | Target finish turns red once the date has passed and Status is not Done.
5 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Phases
Job | Customer | Phase | Crew / sub | Start | Target finish | Inspection | Status | Notes
P-2611 | Grady | Gunite | ShotCrete Pros | 2026-10-11 | 2026-10-12 | Not required | Done | Cure 7 days, water twice daily
P-2611 | Grady | Tile & coping | Coastal Tile | 2026-10-19 | 2026-10-23 | Not required | Not started
P-2614 | Okafor | Steel | In-house crew B | 2026-10-10 | 2026-10-12 | Scheduled | In progress | Steel inspection tomorrow 9am
P-2614 | Okafor | Plumbing & electrical | AquaFlow + Bright Electric | 2026-10-14 | 2026-10-17 | Scheduled | Not started | Bonding inspection with plumbing
P-2620 | Patel | Dig | Delgado Excavation | 2026-10-16 | 2026-10-17 | Not required | Not started | Locate utilities called in

## Summary
Item | Value | Notes
Overview
Entries | 5
Overdue (target finish) | 0
By status
Status: Not started | 3
Status: In progress | 1
Status: Done | 1