## How to use
Print Production Schedule
A free print production spreadsheet: slot jobs by press and day with run time and conflict highlighting in Google Sheets and Excel.
Quick start
1 | Open the Press schedule tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | End time adds changeover (about 9 minutes per screen) and run time; Press conflict turns red when jobs overlap on a press (Auto 1 here).
3 | Jobs still waiting on art should not be slotted early in the day.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Press schedule
Date | Press | Start | Job # | Customer | Pieces | Colors | Pieces per hour | Status | Changeover hours | Run hours | End | Press conflict
2026-10-14 | Auto 1 (8-color) | 7:00 | 2214 | Lakeside 5K | 300 | 4 | 450 | Screens burned | 0.6 | 0.67 | 8:16 | 0
2026-10-14 | Auto 1 (8-color) | 8:30 | 2219 | Brew Co | 144 | 6 | 350 | Screens burned | 0.9 | 0.41 | 9:49 | 0
2026-10-14 | Auto 2 (6-color) | 7:00 | 2220 | Hope Church | 500 | 1 | 600 | Scheduled | 0.15 | 0.83 | 7:59 | 0
2026-10-14 | Manual 1 | 9:00 | 2223 | Band merch | 48 | 3 | 90 | Art pending | 0.45 | 0.53 | 9:59 | 0
2026-10-15 | Auto 1 (8-color) | 7:00 | 2225 | Tech Expo | 1200 | 2 | 500 | Scheduled | 0.3 | 2.4 | 9:42 | 0

## Capacity
Item | Value | Notes
Capacity
Press hours scheduled | 7.24
Jobs waiting on art | 1