## How to use
Film Production Budget
A free film budget spreadsheet: track above- and below-the-line costs with estimate-vs-actual and contingency in Google Sheets and Excel.
Quick start
1 | Open the Budget tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Enter the estimate per account from your budget, then actuals as invoices arrive; over-budget lines turn red.
3 | Keep a contingency line (often 10%) and draw from it explicitly rather than hiding overages.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Budget
Account | Line | Category | Estimate | Actual | Notes | Variance | % of estimate used
1100 | Above the line | Story and rights | 2000 | 2000 | Option paid | 0 | 100%
1300 | Above the line | Director | 8000 | 8000 |  | 0 | 100%
1400 | Above the line | Cast | 12000 | 12500 | Overtime day 3 | -500 | 104.2%
2000 | Below the line: production | Camera package | 6500 | 5900 | Rental deal | 600 | 90.77%
2100 | Below the line: production | Locations and permits | 4000 | 4600 | Extra permit day | -600 | 115%
2200 | Below the line: production | Catering and craft | 3000 | 2700 |  | 300 | 90%
3000 | Below the line: post | Editorial | 7000 | 3500 | In progress | 3500 | 50%
3100 | Below the line: post | Sound and music | 4500 | 0 |  | 4500 | 0%
4000 | Other | Insurance | 2500 | 2500 |  | 0 | 100%
4100 | Other | Contingency (10%) | 5000 | 0 |  | 5000 | 0%

## Totals
Item | Value | Notes
Budget
Total estimate | 54500
Spent to date | 41700
Remaining | 12800
By line
Above the line | 22000
Watch
Lines over budget | 2