## How to use
Project Budget Tracker
A free project budget spreadsheet: track budget vs. actual with variance and percent-spent alerts by line item in Google Sheets and Excel.
Quick start
1 | Open the Budget lines tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Enter the approved budget per line, then update Actual from invoices and timesheets.
3 | Variance turns red when a line is over budget and % spent goes amber at 85%. The Roll-up tab totals by category.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Budget lines
Category | Line item | Owner | Budget | Actual | Variance | % spent
Labor | Internal team (3 FTE × 4 mo) | PMO | 96000 | 71500 | 24500 | 74.48%
Contractors | UX research agency | Design | 18000 | 18900 | -900 | 105%
Software | Licenses – analytics stack | IT | 12400 | 9800 | 2600 | 79.03%
Hardware | Test devices | QA | 4500 | 3950 | 550 | 87.78%
Travel | Customer site visits | Product | 6000 | 2100 | 3900 | 35%
Other | Launch event | Marketing | 8000 | 0 | 8000 | 0%

## Roll-up
Item | Value | Notes
Actual by category
Labor | 71500 | Actual spend by category.
Software | 9800
Hardware | 3950
Contractors | 18900
Travel | 2100
Other | 0
Project
Total budget | 144900
Total spent | 106250
Remaining | 38650
Overall % spent | 73.33%