## How to use
Project Gantt Chart
A free Gantt chart spreadsheet that auto-draws timeline bars from your dates, with owners and progress, in Google Sheets and Excel. No add-ons.
Quick start
1 | Open the Timeline tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Enter each task's owner, start and end dates, and % complete. The Wk columns draw a bar for every week the task spans.
3 | Set Week 1 starts on the Settings tab to move the timeline. End turns red when a task runs late and isn't 100% complete.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Timeline
Task | Owner | Start | End | % complete | Days | State | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8
Kickoff and requirements | Maya | 2026-09-29 | 2026-10-05 | 100% | 7 | Done | ■
Design mockups | Leo | 2026-10-05 | 2026-10-16 | 70% | 12 | In progress | ■ | ■ | ■
Backend API | Sam | 2026-10-10 | 2026-10-31 | 25% | 22 | In progress |  | ■ | ■ | ■ | ■
Frontend build | Priya | 2026-10-17 | 2026-11-07 | 0% | 22 | Not started |  |  | ■ | ■ | ■ | ■
QA and bug fixes | Leo | 2026-11-02 | 2026-11-14 | 0% | 13 | Not started |  |  |  |  | ■ | ■ | ■
Launch | Maya | 2026-11-15 | 2026-11-17 | 0% | 3 | Not started | [6 empty] | ■ | ■
Formulas:
State = IF([Task]="","",IF((E2>=1),"Done",IF(([Start]>TODAY()),"Not started","In progress")))

## Settings
Item | Value | Notes
Week 1 starts | 2026-09-29 | Set to the Monday the project begins; the Wk columns shift with it.
Tasks done | 1
Tasks late | 0
Overall progress | 32.5%