## How to use
Proposal Deadline Calendar
A free deadline calendar for proposal writers: track RFP due dates with section owners and countdowns in Google Sheets or Excel.
Quick start
1 | Open the Deadlines tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Work back from the submission date: questions, drafts, pricing, review. Due turns red when passed and not done.
3 | Days left turns amber inside a week. Late submissions are almost always rejected; leave a day for portal problems.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Deadlines
Due | Deadline | RFP / client | Type | Owner | Status | Days left
2026-10-16 | Questions to contracting officer | City of Fairview: IT services RFP | Questions due | Dana | In progress | 4
2026-10-21 | Technical approach draft | City of Fairview: IT services RFP | Section draft | Raj | In progress | 9
2026-10-23 | Cost volume | City of Fairview: IT services RFP | Pricing | Client CFO | Not started | 11
2026-10-26 | Red team review | City of Fairview: IT services RFP | Final review | Dana | Not started | 14
2026-10-28 | Upload to portal by 2 PM | City of Fairview: IT services RFP | Submission | Dana | Not started | 16
2026-10-12 | Past performance section | State DOT: outreach | Section draft | Raj | In review | 0
Formulas:
Days left = IF([Due]="","",IF(OR(([Status]="Done"),([Status]="Submitted")),"",([Due]-TODAY())))

## Summary
Item | Value | Notes
Overview
Entries | 6
Overdue (due) | 0
By status
Status: Not started | 3
Status: In progress | 2
Status: In review | 1
Status: Done | 0
Status: Submitted | 0