## How to use
Rehearsal Schedule Planner
A free rehearsal planner for theater: schedule scene calls around actor conflicts and mark off-book progress in Sheets or Excel.
Quick start
1 | Open the Rehearsals tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Call only the actors each scene needs; list conflicts so you can adjust the order of work.
3 | Post the schedule weekly and confirm venue access for weekend rehearsals.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Rehearsals
Date | Start | End | Venue | Scenes / numbers | Called actors | Actors with conflicts | Readiness | Hours | Conflict flag | Days to opening
2026-10-14 | 19:00 | 21:30 | Rehearsal hall | Act 1, sc 1-3 | Maria, Tony, ensemble |  | Blocking | 2.5 |  | 44
2026-10-16 | 19:00 | 21:30 | Rehearsal hall | "Tonight" and balcony scene | Maria, Tony | Tony (late, 7:45) | Working | 2.5 | Conflicts: adjust call | 42
2026-10-18 | 10:00 | 14:00 | Main stage | Dance at the gym | Full ensemble | Ben O. | Blocking | 4 | Conflicts: adjust call | 40
2026-10-21 | 19:00 | 22:00 | Main stage | Act 1 run | All Act 1 |  | Run | 3 |  | 37

## Show
Item | Value | Notes
Show
Production | West Side Story
Opening night | 2026-11-27
Totals
Rehearsal hours scheduled | 12
Rehearsals with conflicts | 2