## How to use
Home Renovation Budget
A free renovation budget spreadsheet: track estimated vs. actual spend by room with contingency and payment tracking in Sheets and Excel.
Quick start
1 | Open the Budget tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Set the budget per line before work starts, then log actual (committed) cost and what has been paid.
3 | Spend the contingency line by moving money from it into the lines that ran over.
4 | Enter Budget once, then update Actual as money goes out. Remaining turns red when a line is over budget.
5 | The Summary tab keeps running totals and counts. It updates as you add rows.
6 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Budget
Room | Line item | Budget | Actual | Paid to date | Vendor | Remaining | % used
Kitchen | Cabinets | 14000 | 15250 | 7600 | Cabinet Co | -1250 | 108.9%
Kitchen | Countertops | 4500 | 4380 | 2190 | Stone Works | 120 | 97.33%
Kitchen | Appliances | 6000 | 5640 | 5640 | Best Appliance | 360 | 94%
Primary bath | Tile and labor | 5200 | 6100 | 3000 | Rivera Tile | -900 | 117.3%
Primary bath | Vanity and fixtures | 2400 | 2190 | 2190 | Ferguson | 210 | 91.25%
Whole house | Electrical upgrades | 3800 | 3800 | 1900 | Bright Electric | 0 | 100%
Whole house | Permits | 900 | 860 | 860 | City | 40 | 95.56%
Contingency | 10% reserve | 3700 | 0 | 0 |  | 3700 | 0%

## Summary
Item | Value | Notes
Overview
Entries | 8
Totals
Total budget | 40500
Total actual | 38220
Total paid to date | 23380
Total remaining | 2280