## How to use
Renovation Timeline
A free renovation timeline spreadsheet: sequence phases, trades, and tasks with status tracking to keep a remodel on schedule, in Sheets and Excel.
Quick start
1 | Open the Timeline tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Enter each task with start, duration and what it depends on; End turns red when passed and the task is not done.
3 | Inspections gate the next phase; book them as soon as rough-in is done.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Timeline
Phase | Task | Trade / contractor | Start | Days | Depends on | Status | Cost | End
Design and permits | Kitchen design and permit | Designer | 2026-09-03 | 21 |  | Done | 2400 | 2026-09-24
Demo | Remove cabinets and drywall | GC crew | 2026-10-01 | 3 | Permit | Done | 1800 | 2026-10-04
Rough-in | Move sink drain and supply | Plumber | 2026-10-05 | 3 | Demo | Done | 2600 | 2026-10-08
Rough-in | New circuits and lighting | Electrician | 2026-10-07 | 4 | Demo | In progress | 3400 | 2026-10-11
Inspections | Rough plumbing and electrical inspection | City inspector | 2026-10-14 | 1 | Rough-in | Waiting | 0 | 2026-10-15
Close-up | Insulate and drywall | Drywall sub | 2026-10-16 | 5 | Inspection | Not started | 3200 | 2026-10-21
Finishes | Cabinets and counters | Cabinet installer | 2026-10-25 | 5 | Drywall | Not started | 14000 | 2026-10-30
Punch list | Walkthrough and fixes | GC | 2026-11-06 | 3 | Finishes | Not started | 0 | 2026-11-09
Formulas:
End = IF([Phase]="","",([Start]+[Days]))

## Project
Item | Value | Notes
Project
Project | Hollis kitchen
Budget | 36000
Money
Cost committed | 27400
Remaining budget | 8600
Schedule
Tasks late | 1
Estimated finish | 2026-11-09