## How to use
Restoration Budget Tracker
A free budget tracker for classic car restoration: compare budget vs. actual by category with a running total in Google Sheets or Excel.
Quick start
1 | Open the Budget tab and replace the sample rows with your own — one row per entry. Formulas fill in automatically for new rows.
2 | Budget each category up front; restorations almost always run over in body and paint, so pad it.
3 | Remaining turns red for categories over budget; % used turns amber at 90%.
4 | Keep a backup copy before restructuring columns; renaming a header is safe, deleting a column used in formulas is not.
Colour key
Yellow cells: type your numbers here.
Grey cells: calculated automatically. Leave them alone.
Red highlight: overdue or below a limit. Needs attention.
Amber highlight: getting close. Check soon.
Sample rows are examples. Overwrite or delete them. Formulas extend to new rows automatically. Works in Excel and Google Sheets (File → Import).

## Budget
Category | Item | Budget | Spent | Vendor | Remaining | % used
Body and paint | Media blast, rust repair, paint | 14000 | 15800 | Coastal Kustoms | -1800 | 112.9%
Engine | 350 rebuild | 6500 | 5900 | Machine shop | 600 | 90.77%
Drivetrain | TH350 rebuild + driveshaft | 2800 | 2650 | Trans shop | 150 | 94.64%
Suspension and brakes | Front disc conversion, bushings | 2200 | 2400 | Classic Parts | -200 | 109.1%
Interior | Seats, carpet, headliner | 3800 | 1450 | Upholstery shop | 2350 | 38.16%
Electrical | New harness | 1100 | 0 |  | 1100 | 0%
Chrome and trim | Bumpers re-chromed | 2400 | 0 | Plating shop | 2400 | 0%

## Totals
Item | Value | Notes
Project
Total budget | 32800
Spent so far | 28200
Remaining | 4600